## Test cases
Functionality/UC | Test Scenario | Test Id | Test step# | Action | Expected result | Actual result | Test Status | Testing comments | Client Review comments
Order processing screen fields verification | Order processing screen is accessible from the left hand side menu and it has all the sections as per design document | TC#1 | 1 | user enters the application web url into the browser to access the application | user should be able to access the application through the web url | User is able to login with valid credentials | Pass
|  | TC#1 | 2 | validate if order processing screen is loaded and visible to the user | Order processing screen should load | Order processing screen loaded successfully | Pass
|  | TC#1 | 3 | verify if order processing page is divided into 3 vertical adjacent frames (in addition to the menu) - - Search frame - Submitted Orders - Approved Orders | All 3 frames should be visible to the user adjacent to each other and in below sequence (after menu) - - Search frame - Submitted Orders - Approved Orders | As expected. | Pass | Costemic defects may occur | good (minor changed in red)
|  | TC#1 | 4 | Verify if the message showing time left to next match is visible at the top of the screen in Red color and displays text as - <hrs> Hours to next match <date> @ <time> <time format> e.g. 3 hours to next match Tues 12 Sept@ 12:00 est | message showing time left to next match should visible at the top of the screen in Red color and should displays text as - <hrs> Hours to next match <date> @ <time> <time format> |  | N/A | Post POC implmentation | good
main menu frame of Order processing screen | To verify that left hand side menu has all the fields as per the design doc | TC#2 | 1 | verify if the user name of the logged in user is displayed on the top of left hand side menu options | logged in user name should display on the top of left hand side menu options | Logged in user logo is displayed successfully | Pass
|  | TC#2 | 2 | verify if the main menu has following menu options in order: - Portal - Bank Profile - Customer Profile - Order Processing - Equalization Settlement - Interest payments - Reporting - Fees | main menu should consists of following menu option in order - - Portal - Bank Profile - Customer Profile - Order Processing - Equalization Settlement - Interest payments - Reporting - Fees | As expected. | Pass
|  | TC#2 | 3 | Click on Order Processing option from the main menu and verify if the 'Current Orders' label is placed below the 'Order Processing' label and is left aligned | Current Orders' label should be placed below the 'Order Processing' label and is left aligned |  | N/A | Post POC implmentation
|  | TC#2 | 4 | Validate if the 'Current Orders' field has value calculated in US dollars as per formula : Current Orders = Aggregate of the Principal Amount for all orders listed under Submitted Orders panel + Aggregate of the Principal Amount for all orders listed under Approved Orders panel, displayed at 2 decimal places | Current Orders' field results (USD) = Total Principal Amount from Submitted Orders panel + Total Principal Amount from Approved Orders panel , displayed at 2 decimal places |  | N/A | Post POC implmentation | changed in red
|  | TC#2 | 5 | Verify if the number of orders is displayed as pill next to the Order Processing label and is right aligned. Number is calculated as total count of Current Orders = number of orders from Submitted Orders panel + number of orders from Approved Orders panel | number of orders should display next to the Order Processing label and is right aligned. Number should be calculated as Current Orders = Submitted Orders + Approved Orders |  | N/A | Post POC implmentation | What is this? Is this the pill? If so, then total count = number of orders from Submitted Orders panel + number of orders from Approved Orders panel. Use the word 'pill' or 'badge'
|  | TC#2 | 6 | Verify that the value in 'Submitted Orders' = Aggregate Principal Amount from all orders listed under Submitted Orders panel, displayed at 2 decimal places | Value in 'Submitted Orders' = Aggregate of Principal Amount from all orders listed in Submitted Orders' panel, displayed at 2 decimal places | As expected. | Pass |  | Added
|  | TC#2 | 7 | Verify that the value in 'Approved Orders' = Aggregate Principal Amount from all orders listed under Approved Orders panel (note, if there are no approved orders, then the calculation should equal $0.00), displayed at 2 decimal places | Value in 'Approved Orders' = Aggregate of Principal Amount from all orders listed in Approved Orders' panel, displayed at 2 decimal places | As expected. | Pass |  | Added
|  | TC#2 | 8 | Verify that 'Potential Submitted Orders' = 'Submitted Orders' based on calculation for 'Submitted Orders', displayed at 2 decimal places | Value in 'Potential Submitted Orders' = 'Submitted Orders' based on calculation for 'Submitted Orders', displayed at 2 decimal places | As expected. | Pass |  | Added
|  | TC#2 | 9 | Verify that 'Potential Approved Orders' = 'Approved Orders' based on calculation for 'Approved Orders' | Value in 'Potential Approved Orders = 'Approved Orders' based on calculation for 'Approved Orders' | As expected. | Pass |  | Added
UC.1 | Select, Review and Prioritize Customer Orders Prior to Approval for Potential Submitted Orders and Potential Approved Orders | TCUC01_03 | 1 | login to the TBS system and navigate to the Order Processing screen | User should navigate to the Order Processing screen | User is able to login with valid credentials | Pass
|  | TCUC01_03 | 2 | Click <Select All>, from the left side of the order processing screen | All checkboxes under the Submitted Orders panel from the Order processing screen are highlighted. | As expected. | Pass |  | changed in red
|  | TCUC01_03 | 3 | verify <Select All> is replaced by <Deselect All> and is clickable | <Select All> has been replaced by <Deselect All> and is clickable | As expected. | Pass |  | good
|  | TCUC01_03 | 4 | verify <Approve Selected> button is enabled | <Approve Selected> button is enabled | As expected. | Pass |  | good (minor changed in red)
|  | TCUC01_03 | 5 | Verify that System calculates ‘Potential Submitted Orders’ for the orders selected and displays results (w/ 2 decimal places) | Potential Submitted Orders' value is reduced by the Principal Amount for each order selected (Note - value = $0.00, for all orders selected). - displayed at 2 decimal places |  | Pass | defect#19 | changed in red
|  | TCUC01_03 | 6 | Verify that System calculates ‘Potential Approved Orders’ for the orders selected and displays results (w/2 decimal places) | Potential Approved Orders' value is increased by the Principal Amount for each order selected . - displayed at 2 decimal places |  | Pass | defect#19 | changed in red
|  | TCUC01_03 | 7 | User unchecks some of the check boxes | check boxes displayed as unchecked | As expected. | Pass |  | good (minor changed in red)
|  | TCUC01_03 | 8 | verify if System recalculates ‘Potential Submitted Orders’ per deselection | Potential Submitted Orders' value is increased by the Principal Amount for each order deselected . |  | Pass | defect#19
|  | TCUC01_03 | 9 | verify if System recalculates ‘Potential Approved Orders' per deselection. | Potential Approved Orders' value is reduced by the Principal Amount for each order deselected |  | Pass | defect#19 | Added
|  | TCUC01_03 | 10 | verify <Deselect All> is replaced by <Select All> and is clickable | <Deselect All> should replaced by <Select All> and should be clickable | As expected. | Pass |  | good
|  | TCUC01_03 | 11 | Click <Select All> again, from the left side of the order processing screen | Checkboxes under the Order processing screen should get highlighted per customer order selected and recalculates 'Potential Submitted Orders' and 'Potential Approved Orders' |  | Fail | defect#26 has been deferred | good
UC2 | Approve customer orders for match processing | TCUC02_04 | 1 | login to the TBS system and navigate to the Order Processing screen | User lands on the Order Processing screen | As expected. | Pass
|  | TCUC02_04 | 2 | Click <Select All>, from the left side of the order processing screen | All Checkboxes are highlighted in Submitted Orders panel | As expected. | Pass |  | good (minor changed in red)
|  | TCUC02_04 | 3 | Click <Approve Selected> button and validate if customer orders (selected) from the Submitted Orders panel have moved to the Approved Orders panel | Customer orders selected from the Submitted Orders panel have been transferred to the Approved Orders panel | As expected. | Pass
|  | TCUC02_04 | 4 | Verify if a message 'There are no current Submitted Orders' is displayed | A message 'There are no current Submitted Orders' is displayed | As expected. | Pass |  | good - note (this is fine, only if <Select All> has been clicked and approved.)
|  | TCUC02_04 | 5 | verify if <Select All> and <Approve Selected> are disabled (this is fine, if <Select All> has been clicked and approved.) | <Select All> and <Approve Selected> are disabled | As expected. | Pass |  | good - note (this is fine, only if <Select All> has been clicked and approved.)
|  | TCUC02_04 | 6 | Verify approved Customer orders have a ‘pending’ status until the match process begins | this is for backend purposes. Approved orders are in pending status until the match process is triggered. 'Pending status is not displayed' |  | N/A | this is for backend purposes. Approved orders are in pending status until the match process is triggered. 'Pending status is not displayed' | Note - this is for backend purposes. Approved orders are in pending status until the match process is triggered. 'Pending status is not displayed'
|  | TCUC02_04 | 7 | Validate that System recalculates the ‘Submitted Orders’ attribute: ‘Submitted Orders’ as Amount is reduced by the aggregate of the Principal Amount per customer order approved. | System should recalculates the ‘Submitted Orders’ attribute | As expected. | Pass |  | good
|  | TCUC02_04 | 8 | Validate that System recalculates the ‘Approved Orders’ attribute: ‘Approved Orders’ as Amount will increase by the aggregate of the Principal Amount per customer order approved. | System should recalculates the ‘Approved Orders’ attribute | As expected. | Pass |  | good
|  | TCUC02_04 | 9 | Validate that System recalculates the ‘Potential Submitted Orders’ attribute: ‘Potential Submitted Orders’ as Amount is reduced by the aggregate of the Principal Amount per customer order approved. | System should recalculates the ‘Potential Submitted Orders’ attribute |  | Fail | defect#26 has been deferred | good
|  | TCUC02_04 | 10 | Validate that System recalculates the ‘Potential Approved Orders’ attribute: ‘Potential Approved Orders’ as Amount will increase by the aggregate of the Principal Amount per customer order approved. | System should recalculates the ‘Potential Approved Orders’ attribute |  | Fail | defect#26 has been deferred | good
|  | TCUC02_04 | 11 | Validate that System recalculates the ‘Current Orders’ attribute: ‘Current Orders’ as aggregate of the Principal Amount for all orders listed under the Submitted Orders panel plus the Aggregate of the Principal Amount for all orders listed under the Approved Orders panel. | System should recalculates the ‘Current Orders’ attribute |  | N/A | Post POC implmentation | good
|  | TCUC02_04 | 12 | Validate (pill or badge) is recalculated to = the total count of number of orders in Submitted Orders panel. | Pill or badge reflects the correct number of orders | As expected. | Pass |  | Added
|  | TCUC02_04 | 13 | Validate (pill or badge) is recalculated to = the total count of number of orders in Approved Orders panel. | Pill or badge reflects the correct number of orders | As expected. | Pass |  | Added
UC3 | Conduct Match | TCUC3_05 | 1 | follow TCUC02_04 |  | As expected. | Pass
|  | TCUC3_05 | 2 | User manually triggers the match process (for POC demo) by clicking on countdown clock on the screen | Match process is triggered and System is processing approved orders | As expected. | Pass |  | good
|  | TCUC3_05 | 3 | Verify if a message on the screen that reads ‘Processing Matches’ is displayed (The message will remain until the matching engine has completed processing) | Processing Matches is displayed on the screen | As expected. | Pass |  | good, with minor changes
|  | TCUC3_05 | 4 | Verify if the customer orders from the Approved Orders panel are moved to the Matched Orders panel after processing all matches | Approved Orders is transferred to the Matched Orders panel | As expected. | Pass |  | good
|  | TCUC3_05 | 5 | Verify on completion of matching, countdown clock reset to next match | countdown clock should reset to next match |  | N/A | Can't be tested | good
|  | TCUC3_05 | 6 | Verify if the status of the orders processed by the matching engine will appear as follows: e.g. a. $500,000 allocated out of $500,000 means the order has been 100% filled (For POC demo, we will assume happy path scenario – orders 100% filled) | Orders should be 100% filled | As expected. | Pass |  | good - correct - for POC purposes, all matches are 100% filled
|  | TCUC3_05 | 7 | Verify that system recalculates the ‘Approved Orders’ attribute and Amount reduced by the aggregate Principal Amount of the orders submitted to the match process. | Approved Orders amount should get reduced by the aggregate Principal Amount of the orders submitted to the match process. | As expected. | Pass |  | good
|  | TCUC3_05 | 8 | Verify that system displays ‘Matched Orders’ attribute on the left-hand panel of the Order Processing screen (underneath ‘Approved Orders’) and performs calculation. | The value amount (displayed at 2 decimal places) for the Matched orders attribute - increased by the aggregated Principal Amount of the approved orders submitted to the match process |  | Pass |  | good (minor changed in red)
|  | TCUC3_05 | 9 | Verify that 'Matched Banks' attribute is calculated as a total count of the number of banks the customer’s Principal Amount has been allocated to based on results from the matching algorithm | Verify total count for 'Matched Banks' attribute (verification dependent on use case 4) | As expected. | Pass |  | good
|  | TCUC3_05 | 10 | Validate (pill or badge) is calculated to = the total count of number of orders in Matched Orders panel. | total count = number of orders in the Matched Orders panel |  | N/A | Post POC implmentation | Added
UC4 | Review Post Matched Results | TCUC04_06 | 1 | follow TCUC3_05 |  |  | Pass |  | TCUC04_06
|  | TCUC04_06 | 2 | User selects a bank from the Matched Order panel and clicks '>' to review the allocations | user is able to select a bank from the Matched Order panel and is able to click '>' to review the allocations in detail | As expected. | Pass
|  | TCUC04_06 | 3 | Verify if the screen expanded and displays Maturity Date of the CD and the names of the banks its customer has been allocated to. | Screen should display Maturity Date of the CD and the names of the banks its customer has been allocated to. | As expected. | Pass |  | You made need to break this up per scenario
|  | TCUC04_06 | 4 | Verify that the principal amount allocated to each bank = the aggregate principal amount for the order filled. E.g. principal amount = $1M, it is distributed among 4 banks with $250K chunk to each bank | Principal amount should be allocated to each bank = the aggregate principal amount for the order filled. | As expected. | Pass
|  | TCUC04_06 | 5 | Verify The number of banks the customer has been allocated to = total count for 'Matched Banks' E.g. principal amount = $1M, it is distributed among 4 banks with $250K chunk to each bank | Verify The number of banks the customer has been allocated to = total count for 'Matched Banks' | As expected. | Pass
|  | TCUC04_06 | 6 | User clicks on the Matched Orders panel | Expanded screen should collapse | As expected. | Pass |  | good
|  | TCUC04_06 | 7 | clicks the ‘Corda view’ button at the bottom right side of the Matched Orders panel. | Expanded screen should display the Placed view and received view (info defaulted to "placed" view) | As expected. | Pass |  | good
|  | TCUC04_06 | 8 | Verify the output from the 'Placed' view contains the following fields: Customer Name TIN (Masked) Corda ID CD ID Principal Amount Accrued Interest Maturity Date | View should contain the correct output in correct format | As expected. | Pass | defect# 34-37 | good
|  | TCUC04_06 | 9 | Regulator clicks 'Received' | Received' contents are displayed | As expected. | Pass |  | Added
|  | TCUC04_06 | 10 | Verify the output from the 'Received' view contains the following fields: Customer Name (Masked) TIN (Masked) Corda ID CDID Principal Accrued Interest Maturity Date | View should contain the correct output values as per given in the requirement specification and should be in correct format. |  | Pass |  | good
UC5 | Regulator view only access to Digital ledger | TCUC5_07 | 1 | login to the TBS system as a regulator | User should navigate to the Banks summary screen | As expected. | Pass
|  | TCUC5_07 | 2 | User clicks on the '>' of one the listed banks | Expanded panel of the selected bank should open |  | N/A | Corda view is directly presented to the user | good
|  | TCUC5_07 | 3 | Verify if the expanded section has following fields - Principal Accrued Interest Interest Due at Maturity Last Maturity Date | Expanded section should contain fields - Principal Accrued Interest Interest Due at Maturity Last Maturity Date |  | N/A | Post POC implmentation | good
|  | TCUC5_07 | 4 | User clicks the Corda View button | A regulator view of ledger should load |  | N/A | Corda view is directly presented to the user | good
|  | TCUC5_07 | 5 | Verify if user is able to view the ledger records | user should be able to view the ledger records | As expected. | Pass |  | good